## Stakeholders
Stakeholder | Description | Interest (1-5) | Power/Authority (1-5) | Key Interests | Power/Authority Explanation | Engagement Strategy & Actions
Bristol City Council / Planning Authorities | Local authority responsible for planning permissions, regulatory compliance, and environmental oversight. | 5 | 5 | - Compliance with environmental laws. - Minimising community disruption. - Ensuring long-term sustainability. | Holds legal authority to approve or deny planning applications, issue permits, and enforce compliance with local regulations. Can halt the project for non-compliance. | - Engage early and regularly to avoid delays. - Provide detailed environmental and planning reports. - Ensure compliance with all regulations throughout the project stages.
Regulatory Bodies (Health & Safety Executive, Environmental Agencies) | National and local regulatory bodies responsible for ensuring the project complies with health, safety, and environmental regulations. | 4 | 5 | - Compliance with safety regulations. - Minimising environmental impact. - Avoiding accidents or harm to local residents. | Can issue fines, halt the project, or enforce legal standards related to health, safety, and environmental protection. | - Ensure that all project practices follow regulatory guidelines. - Conduct regular safety and environmental audits. - Submit reports on project safety and environmental impact.
Environmental Officer | Oversees environmental standards and ensures that the project meets sustainability goals (e.g., carbon reduction). | 5 | 4 | - Reducing carbon footprint. - Avoiding damage to local ecosystems. - Preventing contamination (soil, water). | Can enforce environmental regulations, halt the project if environmental standards are violated, and ensure long-term sustainability goals are met. | - Conduct environmental impact studies. - Provide regular updates on sustainability performance. - Engage in public forums to discuss environmental outcomes.
Investors / Financial Backers | Those providing financial resources for the project, including city funding, grants, or private investors. | 4 | 4 | - Financial return on investment (ROI). - Project feasibility and cost control. - Sustainable returns via energy savings. | Can influence budget, timelines, and scope by controlling the financial resources. Can pull out if financial objectives are not met. | - Provide regular financial updates, showing cost control and ROI. - Highlight contingency plans for cost overruns. - Provide projections for long-term energy savings.
Bristol Energy Network / Green Bristol Groups | Local organisations dedicated to promoting renewable energy and reducing Bristol’s carbon footprint. | 4 | 4 | - Supporting renewable energy initiatives. - Tracking the project’s contribution to carbon reduction. - Advocating for local energy savings and long-term sustainability. | Can act as influencers by promoting or criticising the project in terms of sustainability and green energy contributions. They can rally public support or opposition. | - Involve them in discussions about the project’s renewable energy contributions. - Share case studies on energy savings and carbon reduction. - Offer public demonstrations of the system once installed.
Utility Providers (Gas, Electricity, Water) | Utility companies providing infrastructure support for electricity, water, and gas services. May need to approve connections or provide upgrades. | 3 | 4 | - Timely and safe service connection. - Ensuring all connections meet technical and safety standards. | Holds significant influence over the project by controlling service connections, upgrades, and service modifications. Can delay or stop project progress if connections are not approved. | - Engage early to secure necessary utility approvals. - Coordinate timelines to avoid delays. - Ensure all utility modifications meet safety standards.
Suppliers and Contractors | Companies supplying materials (e.g., heat pumps, piping) and services (e.g., drilling, installation) for the GSHP project. | 2 | 4 | - Timely delivery of materials. - Clear timelines to avoid project delays. - Minimising supply chain disruptions. | Controls material and equipment supply for the project. Delays or issues with suppliers can halt progress or increase costs. | - Maintain close communication with suppliers. - Build in contingencies for supply chain delays. - Ensure strict quality control through regular meetings.
Tenants of Barton House | Residents who will benefit from reduced heating costs, improved heating services, and long-term energy savings. | 5 | 3 | - Reliable and lower-cost heating. - Minimal disruption during installation. - Positive long-term benefits (e.g., cost savings). | Can affect the project’s reputation through complaints or negative feedback. Their cooperation is essential for ensuring satisfaction with project outcomes. | - Hold tenant information sessions and forums. - Provide clear timelines and information on noise, dust, or service outages. - Offer compensation or benefits for disruptions.
Local Environmental Activists / NGOs | Groups focused on protecting the local environment and wildlife, as well as promoting sustainable development. | 5 | 3 | - Protecting local ecosystems. - Ensuring sustainability is central to the project. - Avoiding pollution or environmental degradation. | Can raise public awareness and create negative press if the project is perceived to harm the environment. Can apply pressure on the council and environmental officers. | - Engage with them early to share environmental assessments. - Provide transparency on how the project benefits the environment. - Offer forums for input and show responsiveness to concerns.
Community Engagement Groups | Local groups representing the interests of the broader community. They may focus on social, environmental, or economic concerns related to the project. | 4 | 3 | - Transparent project communication. - Minimising disruption to daily life. - Ensuring project is environmentally responsible. | Can influence public opinion, potentially mobilising community support or opposition, impacting the project’s reputation and progress. | - Host regular public meetings. - Provide clear communication on the project’s environmental benefits and community impact. - Address concerns early to avoid public opposition.
Media and Local Press | Local newspapers, radio, and digital platforms that report on significant projects in the area. | 4 | 3 | - Transparency about the project. - Positive stories related to sustainability. - Minimising controversy or disruptions. | Can influence public opinion and shape the narrative around the project. Negative media coverage can result in reputational damage or heightened scrutiny from the public and authorities. | - Prepare regular press releases on project progress. - Highlight positive environmental and social benefits. - Proactively address any concerns to prevent negative coverage.
Local Business Owners | Nearby businesses that may be affected by traffic, noise, or service interruptions during project installation. | 3 | 2 | - Minimising disruptions to business operations. - Ensuring that project work does not impact foot traffic. | Can raise concerns or complaints about traffic, noise, or other disruptions during installation. May put pressure on the council to mitigate these effects. | - Provide clear communication about potential disruptions. - Offer solutions for mitigating impacts (e.g., alternate routes, adjusted installation times). - Provide project updates that benefit businesses long-term (e.g., energy savings).
Broader Local Community | Non-tenants in the surrounding area who may be indirectly affected by noise, traffic, or environmental changes during the project. | 2 | 2 | - Minimising noise and disruption. - Clear communication about environmental impacts. | Can generate local complaints or put pressure on authorities, but generally lacks direct power to influence project decisions. | - Issue public notices about disruptions (e.g., road closures, noise). - Engage only if concerns escalate. - Offer transparency about environmental benefits.

## Risk Register
ID. | Status | Date Raised | Raised by | There is a risk that: | Risk Type (Category) | Unmitigated Consequence | Likelihood (1-5) | Severity (1-5) | Risk Factor (L*S) | Red Risk? (Y/N) | Avoid/Mitigate/Accept | Mitigation/Action(s) | Residual Risk | Risk/Action Owner
1.001 | Open | 2024-10-17 | D Henderson | Drilling encounters unexpected geological conditions | 1 Project | Delays and additional costs for borehole drilling | 3 | 5 | 15 | Y | Mitigate | Conduct detailed site surveys and ground investigation prior to drilling | Additional surveys might be required after initial drilling | Engineering Team
1.002 | Open | 2024-10-13 | G Pyke | Planning permission delays the project | 1 Project | Significant project delays | 2 | 4 | 8 | N | Accept | Engage local authorities early, provide detailed environmental assessments to speed up planning approval | Risk of delays if new regulations arise | Project Manager
1.003 | Open | 2024-10-17 | G Pyke | Noise from drilling operations causes community complaints | 1 Project | Negative public perception and complaints to authorities | 3 | 4 | 12 | N | Mitigate | Limit drilling to daytime hours, use noise-dampening equipment, communicate project timeline to residents | Ongoing risk if delays increase noise levels | Community Engagement Team
1.004 | Open | 2024-10-12 | D Hill | Coordination between contractors and suppliers leads to project delays | 1 Project | Delays in completing borehole drilling, affecting project timeline | 3 | 4 | 12 | N | Mitigate | Hold regular coordination meetings with contractors and suppliers to ensure smooth progress and materials supply | Risk of miscommunication between stakeholders | Procurement & Contractor Team
1.005 | Open | 2024-10-22 | D Hill | Minor delays in procurement of secondary equipment | 1 Project | Minor project schedule adjustments, but no major impact | 2 | 2 | 4 | N | Accept | Build small buffer time for minor procurement delays | Minimal effect on overall timeline | Procurement Team
1.006 | Open | 2024-10-10 | D Hill | Budget overruns due to unforeseen ground conditions | 1 Project | Costs increase, threatening project financial feasibility | 3 | 4 | 12 | N | Accept | Include contingency funds for ground condition risks, conduct detailed surveys pre-project | Risk of exceeding contingency if unexpected issues persist | Finance Manager
2.001 | Open | 2024-10-22 | G Powell | Total cost of the project is underestimated | 2 Financial | Project funding falls short, causing delays or project failure | 3 | 5 | 15 | Y | Mitigate | Create a detailed cost estimation using experienced contractors and suppliers for accurate financial forecasting | Additional costs may emerge due to material or labour increases | Finance Manager
2.002 | Open | 2024-10-12 | D Henderson | Material prices increase unexpectedly due to supply chain issues | 2 Financial | Cost escalation leads to budget overruns and potential funding gaps | 3 | 4 | 12 | N | Accept | Secure long-term contracts with suppliers, include buffer in the budget for price fluctuations | Risk of international events affecting pricing | Procurement & Finance Team
2.003 | Open | 2024-10-12 | G Powell | Project completion takes longer than expected, causing financial strain | 2 Financial | Delays lead to extended labour costs, delaying financial returns | 3 | 4 | 12 | N | Accept | Develop a realistic project timeline with buffer time, monitor progress closely to avoid delays | Risk of unavoidable delays causing additional costs | Project Manager
2.004 | Open | 2024-10-12 | D Henderson | Insufficient financial reserves to cover unexpected risks | 2 Financial | Project halts or scales down, reducing the return on investment | 2 | 5 | 10 | N | Accept | Set aside contingency funds to cover unexpected risks, secure additional funding if necessary | Residual financial risk remains if risks escalate dramatically | Finance Manager
2.005 | Open | 2024-10-17 | G Pyke | Changes in energy prices affect the long-term economic viability of the system | 2 Financial | System operation may not generate enough savings or returns for tenants | 2 | 4 | 8 | N | Accept | Lock in energy price contracts where possible, conduct financial modelling for different energy price scenarios | Energy price volatility may remain beyond project control | Finance & Operations Team
3.001 | Open | 2024-10-13 | G Pyke | Negative public perception due to noise or disruption during drilling operations | 3 Reputation | Complaints from residents, potential protests, or opposition to the project | 3 | 4 | 12 | N | Mitigate | Provide clear communication to the public about the timeline and benefits of the project, offer noise-dampening solutions | Ongoing complaints may arise, but mitigation will reduce their frequency | Community Engagement Team
3.002 | Open | 2024-10-12 | D Hill | Environmental concerns due to perceived risks of groundwater contamination | 3 Reputation | Damaged trust with the community, negative media coverage | 2 | 5 | 10 | N | Mitigate | Perform comprehensive environmental impact studies, publish the findings publicly, engage with local environmental groups | Residual risk remains, but proper environmental oversight will minimise it | Environmental Officer
3.003 | Open | 2024-10-12 | D Henderson | Media coverage of any accidents or delays damages the reputation of the project | 3 Reputation | Negative press coverage leads to community distrust and potential project delays | 3 | 4 | 12 | N | Mitigate | Engage with local media proactively, provide updates and statements during project milestones, focus on positive outcomes | Media coverage may still highlight any negative events | PR & Communications Team
3.004 | Open | 2024-10-10 | D Henderson | Local businesses perceive the project as damaging their foot traffic or revenue | 3 Reputation | Local businesses rally against the project, causing local opposition | 2 | 4 | 8 | N | Mitigate | Meet with local business owners to explain the project’s benefits, offer compensation or marketing support during disruptions | Some businesses may still oppose the project | Community Engagement Team
3.005 | Open | 2024-10-22 | G Powell | Delays or underperformance of the system affects tenant satisfaction | 3 Reputation | Residents feel dissatisfied with the system’s performance, impacting trust | 3 | 4 | 12 | N | Mitigate | Ensure system is properly tested before commissioning, provide clear guidelines for usage and expected savings, communicate openly | Residual dissatisfaction if performance does not meet expectations | Operations & Maintenance Team
3.006 | Open | 2024-10-17 | G Powell | Minor media coverage highlights delays | 3 Reputation | Slightly negative perception but no long-term impact | 2 | 2 | 4 | N | Accept | Provide regular project updates to media, focus on positive milestones | Risk remains if not communicated properly | PR & Communications Team
4.001 | Open | 2024-10-13 | G Powell | Installation errors lead to poor system performance | 4 Quality | Reduced system efficiency and reliability, higher operational costs | 3 | 5 | 15 | Y | Avoid | Use qualified contractors, conduct installation audits, and perform performance tests post-installation | Residual risks remain if errors are not identified early | Installation Contractor
4.002 | Open | 2024-10-17 | D Hill | Boreholes are improperly drilled, affecting system efficiency | 4 Quality | Reduced heating capacity, lower energy savings for residents | 2 | 5 | 10 | N | Mitigate | Conduct ground surveys and ensure proper drilling methods are followed, perform post-drilling inspections | Residual risk if geological conditions are misjudged | Drilling Contractor
4.003 | Open | 2024-10-12 | G Pyke | Manufacturing defects in heat pump units or piping | 4 Quality | Equipment failure, leaks, or reduced efficiency, leading to repair costs | 2 | 5 | 10 | N | Mitigate | Source equipment from reputable manufacturers with strict quality control, inspect all units before installation | Residual risk from rare defects in manufacturing | Procurement & Quality Control
4.004 | Open | 2024-10-17 | G Powell | Lack of regular maintenance reduces the lifespan of the system | 4 Quality | System failures, leading to higher operational costs and dissatisfied tenants | 3 | 4 | 12 | N | Mitigate | Implement a strict maintenance schedule with regular inspections and tune-ups to ensure system longevity | Risk of occasional unplanned failures due to environmental factors | Operations & Maintenance Team
4.005 | Open | 2024-10-22 | D Hill | System fails to meet expected energy efficiency targets | 4 Quality | Tenants face higher heating bills, undermining the project's energy-saving goals | 2 | 5 | 10 | N | Mitigate | Set clear performance standards, conduct thorough performance testing, and provide proper user training | Performance may still vary based on user behaviour | Engineering & Performance Team
4.006 | Open | 2024-10-17 | D Henderson | Minor defects found in non-critical components | 4 Quality | Small operational inefficiencies but no major functional issues | 2 | 2 | 4 | N | Accept | Implement quality checks on non-critical components, replace any minor defective parts | Limited operational impact | Quality Control Team
4.007 | Open | 2024-10-10 | D Hill | Heating dmeand exceeds installed capacity of ground source heat pumps | 4 Quality | Ground source heat pumps cannot supply enough heat | 1 | 5 | 5 | N | Mitigate | There are existing space heaters in many of the properties already | Existing space heaters malfunction. | Quality Control Team
5.001 | Open | 2024-10-12 | D Hill | Delivery of critical drilling equipment is delayed | 5 Supply Chain | Delays in project schedule, increased costs due to labour standby time | 3 | 4 | 12 | N | Mitigate | Source equipment from multiple suppliers, build buffer time into project schedule | Residual risk due to international shipping delays | Procurement Team
5.002 | Open | 2024-10-22 | G Powell | Key materials such as piping or heat pump units are unavailable | 5 Supply Chain | Delays in installation, potential increases in material costs | 3 | 4 | 12 | N | Mitigate | Establish relationships with multiple suppliers, keep stock of essential materials to prevent shortages | Risk remains if global supply chain issues arise | Engineering & Procurement Team
5.003 | Open | 2024-10-10 | G Pyke | Supplier bankruptcy leads to discontinuation of critical components | 5 Supply Chain | Project delays or cost increases due to sourcing alternative suppliers | 2 | 5 | 10 | N | Mitigate | Perform financial due diligence on suppliers, maintain secondary suppliers for critical components | Residual risk due to unforeseen supplier financial difficulties | Procurement Team
5.004 | Open | 2024-10-13 | G Powell | Minor delays in receiving non-critical materials | 5 Supply Chain | Small delays in non-critical activities but no impact on core project tasks | 2 | 2 | 4 | N | Accept | Source non-critical materials with flexible deadlines, ensure alternative suppliers are available | Minor disruptions to non-core tasks | Procurement Team
5.005 | Open | 2024-10-13 | G Pyke | Supplier quality issues result in faulty or delayed shipments | 5 Supply Chain | Delays in project schedule, increased costs due to returns or replacements | 3 | 4 | 12 | N | Mitigate | Establish quality control checks with suppliers, perform inspections on critical shipments | Risk remains if undiscovered defects emerge during installation | Quality Control & Procurement
5.006 | Open | 2024-10-13 | D Hill | Exchange rate fluctuations increase the cost of imported materials | 5 Supply Chain | Increased costs affecting the overall project budget | 3 | 3 | 9 | N | Accept | Hedge against currency fluctuations through forward contracts or buy materials in bulk at fixed rates | Limited control over long-term currency volatility | Finance & Procurement Team
6.001 | Open | 2024-10-12 | G Powell | Data breach from unauthorised access to project management systems | 6 Security | Exposure of sensitive project data, leading to legal or financial consequences | 2 | 5 | 10 | N | Mitigate | Implement strong cybersecurity measures, including encryption, multi-factor authentication, and regular audits | Residual risk of advanced hacking attempts | IT Manager
6.002 | Open | 2024-10-10 | D Henderson | Cyber attack targeting project contractors or suppliers | 6 Security | Disruption of project operations, delays due to compromised contractor systems | 3 | 4 | 12 | N | Mitigate | Ensure contractors adhere to security standards, conduct cybersecurity training for all partners | Cyber threats remain, but can be minimised through vigilant security | IT Manager
6.003 | Open | 2024-10-13 | D Henderson | Unauthorised physical access to the project site | 6 Security | Theft of equipment or vandalism, resulting in delays and increased costs | 2 | 4 | 8 | N | Mitigate | Install fencing, CCTV, and restricted access points at the project site | Residual risk of determined theft attempts | Security Team
6.004 | Open | 2024-10-17 | G Powell | Hackers access tenant data related to energy usage and billing | 6 Security | Tenants' personal data is exposed, leading to legal liabilities | 2 | 5 | 10 | N | Avoid | Ensure tenant data is encrypted and stored securely, implement strict data access controls | Risk of sophisticated cyber attacks remains | IT Manager
6.005 | Open | 2024-10-10 | D Hill | Unauthorised personnel tamper with the GSHP system | 6 Security | Damage to the system, causing operational failures and potential environmental risks | 2 | 5 | 10 | N | Mitigate | Install access control systems and monitoring at all critical system locations, perform regular inspections | Physical security risks remain but can be reduced with monitoring | Security Team
7.001 | Open | 2024-10-12 | D Hill | Drilling impacts groundwater, leading to contamination | 7 Environmental | Water contamination affects local wildlife, flora, and possibly drinking water | 2 | 5 | 10 | N | Avoid | Perform thorough environmental impact assessments and drilling site surveys, follow best drilling practices | Risk remains due to unknown subsurface conditions | Environmental Officer
7.002 | Open | 2024-10-17 | D Henderson | Community opposition due to concerns over environmental impacts | 7 Environmental | Delays and opposition to the project, causing reputational and financial damage | 3 | 4 | 12 | N | Mitigate | Conduct open forums with the community to explain environmental safeguards, share environmental studies | Ongoing risk of public perception if concerns are not addressed | Community Engagement Team
7.003 | Open | 2024-10-22 | G Pyke | Excavated earth and debris during drilling are improperly disposed | 7 Environmental | Harm to local ecosystems, possible legal penalties for improper disposal | 3 | 4 | 12 | N | Avoid | Ensure proper waste management protocols, use licensed disposal services, monitor debris removal processes | Risk remains if improper disposal is not strictly monitored | Environmental Officer
7.004 | Open | 2024-10-12 | G Pyke | Greenhouse gas emissions from machinery during installation | 7 Environmental | Contribution to local air pollution and climate change | 3 | 4 | 12 | N | Mitigate | Use low-emission machinery where possible, reduce on-site fuel consumption, optimise logistics to reduce emissions | Emissions may still occur but can be reduced with better equipment | Operations Team
7.005 | Open | 2024-10-22 | D Henderson | Heat pump operation affects the surrounding ecosystem | 7 Environmental | Changes in soil temperature or water table can impact local wildlife and plant life | 2 | 4 | 8 | N | Mitigate | Conduct thermal modelling to assess the impact of the heat pump operation on local ecosystems | Long-term monitoring required to assess ongoing impact | Environmental Officer
8.001 | Open | 2024-10-22 | G Pyke | Workers face injuries during drilling or heavy machinery operation | 8 Health and Safety | Serious injury or fatality on-site, legal claims, and work stoppages | 2 | 5 | 10 | N | Mitigate | Implement comprehensive health and safety protocols, provide PPE, train workers on safe use of machinery | Residual risk if safety protocols are not followed strictly | Safety Officer
8.002 | Open | 2024-10-12 | G Pyke | Falls, trips, and other site-related accidents during installation | 8 Health and Safety | Injuries to workers, project delays, and legal liabilities | 3 | 4 | 12 | N | Mitigate | Conduct site safety audits, ensure proper signage and walkways, maintain strict housekeeping standards | Risk remains for accidents if safety measures are not enforced | Site Manager
8.003 | Open | 2024-10-10 | D Henderson | Accidental contact with underground utilities during drilling | 8 Health and Safety | Electrical shock, gas leaks, or service interruptions causing injury or damage | 2 | 5 | 10 | N | Mitigate | Perform utility surveys before drilling, use detection equipment, ensure that safety distances are maintained | Risk remains if unknown utilities are not detected | Engineering Team
8.004 | Open | 2024-10-22 | G Pyke | Exposure to harmful substances (e.g., dust or emissions) during installation | 8 Health and Safety | Health impacts on workers or nearby residents, including respiratory issues | 3 | 4 | 12 | N | Mitigate | Implement dust control measures, provide workers with respirators, monitor air quality during construction | Residual risk due to environmental factors | Environmental Officer
8.005 | Open | 2024-10-22 | G Powell | Unsafe system operation leads to overheating or leaks | 8 Health and Safety | Health risks to tenants, potential system failure and injury | 2 | 5 | 10 | N | Mitigate | Perform safety inspections regularly, train maintenance teams, and monitor system performance | Long-term risk of failure if inspections are not regular | Operations & Maintenance Team
8.006 | Open | 2024-10-17 | G Powell | Minor slips or cuts on-site during non-heavy equipment work | 8 Health and Safety | Minor injuries to workers but no major consequences or delays | 2 | 2 | 4 | N | Accept | Ensure all workers have basic safety training and appropriate PPE, maintain clean site conditions | Minor risk remains but is manageable | Site Manager
9.001 | Open | 2024-10-17 | G Pyke | The project disproportionately affects low-income or vulnerable groups | 9 Ethical | Perceived or actual discrimination, leading to community opposition and reputational damage | 2 | 5 | 10 | N | Mitigate | Conduct equity impact assessments, ensure fair communication with all groups, provide support for vulnerable tenants | Residual risk if support is not perceived as adequate | Community Engagement Team
9.002 | Open | 2024-10-12 | D Henderson | Minor complaints about perceived unfairness in community engagement | 9 Ethical | Limited community dissatisfaction but no long-term impact | 2 | 2 | 4 | N | Mitigate | Provide open forums for feedback and address minor concerns early | Complaints may persist but will be handled | Community Engagement Team
9.003 | Open | 2024-10-17 | G Powell | The project does not fully align with sustainability and green energy goals | 9 Ethical | Public perception of "greenwashing," damaging trust and potential project funding | 3 | 4 | 12 | N | Mitigate | Ensure that the project meets sustainability standards, use renewable energy sources for installation and operation | Risk remains if the public feels project falls short of expectations | Sustainability Officer
9.004 | Open | 2024-10-17 | G Pyke | Lack of transparency in project communications with the public | 9 Ethical | Loss of community trust, reputational damage, and possible opposition | 3 | 4 | 12 | N | Mitigate | Maintain open lines of communication with residents, provide regular updates, involve community in key decisions | Risk of misunderstanding or incomplete communication | Community Engagement Team
9.005 | Open | 2024-10-13 | G Powell | Inequitable distribution of project benefits, where some residents benefit more than others | 9 Ethical | Complaints from tenants, potential legal challenges, and reputational damage | 2 | 4 | 8 | N | Avoid | Ensure fair access to benefits (e.g., cost savings) for all tenants, implement equitable pricing structures | Risk remains if tenants perceive inequality in benefits | Project Manager
9.006 | Open | 2024-10-17 | D Henderson | Labour used by suppliers is unethical or exploitative | 9 Ethical | Reputational damage and potential legal ramifications, public opposition | 2 | 5 | 10 | N | Avoid | Vet suppliers carefully, ensure that all suppliers comply with ethical labour standards, conduct regular audits | Residual risk of undetected labour issues in lower-tier suppliers | Procurement Team
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can’t be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can’t be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can’t be used.

## Validation Drop-Down Lists
Status | Risk Type (Category) | Avoid/Mitigate/Accept | Raised By
Open | 1 Project | Avoid | D Hill
Closed | 2 Financial | Mitigate | D Henderson
| 3 Reputation | Accept | G Powell
| 4 Quality |  | G Pyke
5 Supply Chain
6 Security
7 Environmental
8 Health and Safety
9 Ethical

## Project Risk Register (3) (hidden)
ID. | Status | Date Raised | Raised by | There is a risk that: | Risk Type (Category) | Unmitigated Consequence | Likelihood (1-5) | Severity (1-5) | Risk Factor (L*S) | Avoid/Mitigate/Accept | Mitigation/Action(s) | Residual Risk | Risk/Action Owner
1.001 | Open | 2024-03-10 | IC | Lack of clarity about contract means that the Company does not know it is breaching a legal agreement | 1 Project | Legal liability | 1 | 5 | 5 | Avoid | Consult internal and external legal teams (see EM-0003, Section 6) | Live documents can be edited - use version control or wet ink signatures | Lead Engineer
1.002 | Open | 2024-03-10 | WF | Poor memory and poor control of data means information is effectively lost from the project team | 1 Project | Less value added by the Product | 3 | 2 | 6 | Mitigate | Organise physical and digital spaces, and use version control to access past documents (see EM-0007) | Confusion over agreed organisation conventions: train all staff before using these | Quality Manager
1.003 | Open | 2024-04-03 | IC | Customers do not trust an unfamiliar brand name with their medical care, leading to low sales | 1 Project | The Product does not make profit | 2 | 5 | 10 | Mitigate | Marketing team to decide how to utilise familiarity of the Parent Company (see EM-0003, Section 7) |  | Marketing Team
1.004 | Open | 2024-04-03 | IC | Open-access maps data is not already available and needs to be manually created by the software team | 1 Project | Earlier project costs higher than modelled | 2 | 4 | 8 | Accept | Regularly update cost structure (see EM-0003, Section 8) |  | Research and Development
1.005 | Open | 2024-04-03 | IC | Competitor introduces similar or better product before Solas, making the Product obsolete | 1 Project | The Product does not make profit | 2 | 5 | 10 | Mitigate | Release in three shorter phases with increased functionality at each phase, rather than releasing one product at the end of a long development cycle. Accept residual risk of competition (see EM-0003, Section 5) |  | Lead Engineer
2.001 | Open | 2024-02-17 | IC | Reasonable use of the Product is not clearly defined to the customer | 2 Financial | Customer can claim refund or replacement under Consumer Rights Act if damaged after unreasonable use | 3 | 2 | 6 | Avoid | Consult legal team about how to clearly and legally define intended use to customers (see EM-0003, Sections 6 and 7) | N/A | Lead Engineer
2.002 | Open | 2024-04-03 | OD | Total cost is underestimated in cost structure | 2 Financial | The Product cannot be finished, or is finished at a loss to the Company | 3 | 5 | 15 | Avoid | Use a conservative 30% profit margin. Conduct all market research in-house to get the most insight possible into actual costs (see EM-0003, Sections 5 and 8) |  | Lead Engineer
2.003 | Open | 2024-04-03 | OD | Total cost is overestimated in cost structure | 2 Financial | The Product's value is limited by unnecessarily low spending | 3 | 4 | 12 | Mitigate | Review actual costs in financial reviews during each phase. Conduct all R&D in-house to get the most insight possible into actual costs (see EM-0003, Sections 5 and 8) | Some "invisible" costs are not included in the review, leading to underestimated cost (see 1.002) | Lead Engineer
2.004 | Open | 2024-04-20 | IC | The Company cannot secure enough funding to continue with the Product | 2 Financial | The Product cannot be finished, or is finished at a loss to the Company | 3 | 5 | 15 | Avoid | Secure revenue streams early with Phase 1 launch. Cover some costs of subsequent phases with pricing of Phase 1 product (see EM-0003, Sections 5 and 8) |  | Sales
3.001 | Open | 2024-02-17 | IC | Incorrect processing of customer data such as location or medical information lead to a breach of data protection laws | 3 Reputation | Legal liability, reputation of being unsafe | 3 | 5 | 15 | Avoid | Consult legal service about adherence to data protection laws (see EM-0003, Section 6). Be transparent about use, storage and deletion of data. Do not store sensitive user data on any cloud-based locations, and do not take physical copies of data out of the office (see EM-0007). | Risk of malware/phishing attacks, and illegal entry into office building (see 6.001 and 6.002) | CEO
3.002 | Open | 2024-04-15 | MR | The Product does not meet expectations set by marketing, even if it does conform to the Consumer Protection Act | 3 Reputation | Reputation of the Product being disappointing | 3 | 2 | 6 | Mitigate | Marketing team to communicate with engineering team to make sure marketing claims are realistic (see EM-0004) | Misunderstandings during communication | Marketing
4.001 | Open | 2024-04-15 | IC | Quality testing plan is not sufficient to screen out all faulty products | 4 Quality | Some customers are dissatisfied, and costs are incurred from replacing or refunding products | 5 | 2 | 10 | Accept | Review quality metrics, including reported faults, to determine whether the current quality plan is still acceptable (see EM-0007) |  | Quality Manager
4.002 | Open | 2024-02-17 | IC | Due to similarity of customisable parts, items could get confused with each other during manufacturing | 4 Quality | Customer dissatisfaction, financial loss due to requirement to replace or refund | 3 | 3 | 9 | Avoid | Introduce serialisation system in manufacturing process and produce inventory of parts (see EM-0007) | Parts could be mislabelled | Quality Manager
4.003 | Open | 2024-03-10 | IC | In-house manufacturing of housing means responsibility for quality is entirely internal, which could lead to mistakes due to lack of expertise | 4 Quality | Customer dissatisfaction, financial loss due to requirement to replace or refund many parts | 2 | 3 | 6 | Mitigate | Establish quality product and process management systems (see EM-0007) |  | Quality Manager
4.004 | Open | 2024-03-10 | IC | Inadequate communication of design to external manufacturers leads to incorrect product being made | 4 Quality | Large financial loss due to need to re-do manufacturing work | 2 | 5 | 10 | Avoid | Review all CAD drawings and assemblies by senior team member, use version control and signatures to ensure an approved CAD file is sent to manufacturers (see EM-0007) |  | Lead Engineer
4.005 | Open | 2024-03-10 | OD | Inadequate expertise leads to quality loss | 4 Quality | Financial loss due to need to frequently reject parts | 3 | 3 | 9 | Mitigate | Provide sufficient training and guidance to employees (see EM-0007) |  | Quality Manager
ID. | Status | Date Raised | Raised by | There is a risk that: | Risk Type (Category) | Unmitigated Consequence | Likelihood (1-5) | Severity (1-5) | Risk Factor (L*S) | Avoid/Mitigate/Accept | Mitigation/Action(s) | Residual Risk | Risk/Action Owner
5.001 | Open | 2024-04-03 | OD | Supply company can no longer be used (eg. due to increased prices, unacceptable part quality, or complete shutdown) | 5 Supply Chain | Delays to production leading to financial loss | 2 | 4 | 8 | Mitigate | Have a backup supplier for each type of part, whose quality has been approved but which is only to be used in case of failure (see EM-0007) |  | Quality Manager
5.002 | Open | 2024-04-15 | DH | There is a fault with a manufacturing machine that prevents parts from being manufactured correctly | 5 Supply Chain | Supply chain is delayed, preventing profit, while extra repair costs are introduced | 4 | 3 | 12 | Mitigate | Inspect machines regularly to anticipate any faults (see EM-0007) |  | Quality Manager
5.003 | Open | 2024-04-15 | OD | Suppliers do not deliver goods to schedule | 5 Supply Chain | Supply chain is delayed, preventing profit | 4 | 3 | 12 | Mitigate | Conduct supplier approval process to choose a supplier with low likelihood of delays (see EM-0007) |  | Quality Manager
5.004 | Open | 2024-02-17 | DH | Goods are damaged in transit to the customer | 5 Supply Chain | Customer dissatisfaction, financial loss due to requirement to replace or refund | 4 | 2 | 8 | Avoid | Use premium delivery service; Design housing to withstand reasonable impact force (see EM-0007) | Reduced frequency may still get damaged; if this is kept below 1 in 1000 it is acceptable. | Quality Manager
5.004 | Open | 2024-04-15 | OD | A batch of products is damaged due to exceptional transit circumstances (eg a collision) | 5 Supply Chain | Some customers are dissatisfied, and costs are incurred from replacing or refunding products | 1 | 2 | 2 | Accept | Considered exceptional enough to accept (see EM-0007) |  | N/A
5.005 | Open | 2024-04-15 | IC | Goods are damaged in storage | 5 Supply Chain | Some customers are dissatisfied, and costs are incurred from replacing or refunding products | 3 | 2 | 6 | Avoid | Check storage conditions regularly to prevent damaged goods from being sent to customers. Have a storage plan as part of quality management processes (see EM-0007) |  | Quality Manager
6.001 | Open | 2024-02-17 | IC | Phishing attacks on digital locations lead to customer data breach | 6 Security | Legal liability, reputation of being unsafe | 2 | 5 | 10 | Avoid | Delete customer data after 5 days. Train all employees in IT security when they start work. Do not permit employees to access customer data outside of the workplace. Use firewalls and require strong passwords on work computers. If a breach is detected, delete all customer data and take measures to inform all customers immediately. (see EM-0007) | Data could be incorrectly deleted or breached before deletion | IT Manager
6.002 | Open | 2024-02-17 | IC | Illegal entry into physical office space where customer data is stored leads to customer data breach | 6 Security | Legal liability, reputation of being unsafe | 2 | 5 | 10 | Avoid | Install burglar alarms and CCTV, and have a keypad system in place for entry into the office. Protect sensitive spaces by limiting keypad access permissions. Have alarms and CCTV in visible locations outside sensitive spaces as a deterrent. (see EM-0007) |  | IT Manager
6.003 | Open | 2024-04-15 | IC | Identity theft and fraud could take place during payment process for online subscriptions | 6 Security | The Company is liable for customer damages and has a reputation of being unsafe | 2 | 4 | 8 | Avoid | Protect and regulate payment interface (see EM-0007) |  | IT Manager
6.004 | Open | 2024-04-15 | IC | Internal theft of parts or products | 6 Security | Financial loss due to missing goods, possibility of counterfeits being introduced into market, poor reputation if discovered | 1 | 4 | 4 | Avoid | Keep inventory of parts to track numbers, and have clear workplace disciplinary policies for theft (see EM-0007) |  | Human Resources, Quality Manager
7.001 | Open | 2024-04-03 | FH | High volumes of waste are generated in manufacturing process | 7 Environmental | Disposal of waste harms flora/fauna | 3 | 3 | 9 | Accept | Accept that machining process generates waste, but consider this when choosing supplier (see EM-0006) |  | Lead Engineer
7.002 | Open | 2024-04-03 | FH | High volumes of cooling fluid are used in manufacturing process | 7 Environmental | Depletion of natural water reservoirs, putting strain on ecosystems | 3 | 3 | 9 | Accept | Accept that reliability and cost-effectiveness of machining process requires use of cooling fluid, but consider this when choosing supplier (see EM-0006) |  | Lead Engineer
7.003 | Open | 2024-04-03 | FH | Suppliers dispose of waste unsustainably (eg. Pollutants in water reservoirs) | 7 Environmental | Pollution of water and land | 3 | 4 | 12 | Avoid | Conduct due diligence to check disposal risks before approving suppliers, and provide instructions for safe disposal (see EM-0006) |  | Quality Manager
7.004 | Open | 2024-04-03 | FH | There are high greenhouse gas emissions during transport of materials and of finished goods | 7 Environmental | Contribution to greenhouse effect | 4 | 4 | 16 | Mitigate | Remain UK-based in first two phases, and restrict global sales in Phase 3 to the US (see EM-0003, Section 5) |  | CEO
8.001 | Open | 2024-04-15 | IC | There is a workplace accident | 8 Health and Safety | Minor temporary injury | 2 | 4 | 8 | Avoid | Have a health and safety plan as part of quality management processes, and conform to the UK Health and Safety guidelines, including tracking all near-misses (see EM-0007) |  | Quality Manager
ID. | Status | Date Raised | Raised by | There is a risk that: | Risk Type (Category) | Unmitigated Consequence | Likelihood (1-5) | Severity (1-5) | Risk Factor (L*S) | Avoid/Mitigate/Accept | Mitigation/Action(s) | Residual Risk | Risk/Action Owner
8.002 | Open | 2024-04-15 | IC | There is a severe workplace accident | 8 Health and Safety | Permanent injury or death | 1 | 5 | 5 | Avoid | Have a health and safety plan as part of quality management processes, and conform to the UK Health and Safety guidelines, including tracking all near-misses (see EM-0007) |  | Quality Manager
9.001 | Open | 2024-04-15 | IC | The Product and its marketing reinforces negative stereotypes about disabilities | 9 Ethical | Contribution to stigma | 3 | 3 | 9 | Avoid | Consult focus group or charity (see EM-0003, Section 9) |  | Lead Engineer
9.002 | Open | 2024-04-15 | IC | Supply chain involves exploitation of workers | 9 Ethical | Contribution to exploitation, high damage to reputation and potential liability if discovered | 2 | 5 | 10 | Avoid | Use supplier approval process to assess whether labour is fair (see EM-0003, Section 9) |  | Quality Manager
9.003 | Open | 2024-04-15 | IC | Inconsiderate use of AI leads to a biased Product that uses data based on stereotypes about disabilities | 9 Ethical | Harm to customers, potentially dangerous | 4 | 4 | 16 | Avoid | Use AI in image recognition only, not in any health related applications (see EM-0003, Section 9) |  | Lead Engineer
9.004 | Open | 2024-04-27 | IC | Marketing and design of the Product is not well-informed, leading to incorrect assumptions about disabilities | 9 Ethical | Customers alienated by reinforced stigma, and device does not provide value | 4 | 3 | 12 | Avoid | Human Factors study in second phase to ensure that both design and messaging align with reality (see EM-0003, Section 9) |  | Lead Engineer

## Working Area (hidden)
Working Area
Status | Open
Closed
Risk Type | Technical
Health and Safety
Commercial
Project
Treatment | Avoid
Mitigate
Accept